## Sheet1
|  |  | Hours | # Iterations |  | Notes
Total Estimate Hours | 600
Summed Hours | 600
Work Categories | Website Demo | Example Home, About, Certification, and Contact Us pages | 25 | 1 | 25
0
| MFA | Setting up overall MFA structure | 50 | 1 | 50
|  | Configuring MFA for each company | 3 | 50 | 150
0
| Certifications/Engineering Pages | Approx 35 pages of services | 3 | 35 | 105
0
| Design | Perfecting Design | 50 | 1 | 50
0
| Mobile | Implementing React Native and getting on Google Play Store, Apple App Store | 100 | 1 | 100
0
| Additional Pages | Our Values, Careers, Contact Us, What We Do pages - approx 12 pages | 120 | 1 | 120 | These pages will likely take longer than the "certifications/engineering" pages because each page will need more customization.
0